## A3 Problem Solving - Simple
Problem Definition | [5 empty] | A3 | Problem Solving
| Title | [5 empty] | Start Date |  |  | Estimated Completion Date
| Finding parts | [5 empty] | 2024-02-27 |  |  | 2024-03-12
| Problem Description | [5 empty] | Problem Category
[8 empty] | x | Quality |  | Waste and efficiency
[8 empty] | x | Cost |  | Health and safety
[9 empty] | Delivery |  | Customer satisfaction
[9 empty] | Moral |  | Other
| Goal | [5 empty] | Expected Benefits
| Determine best parts | [5 empty] | Smaller, better functioning device
Cause Analysis | Cause and Effect and 5 Whys | [5 empty] | Cause Analysis Summary (Prioritize in order of importance)
|  | Find best websites |  | Haven't contacted engineering sales |  |  | 1. Find best supplier websites
2. Contact engineering sales to reduce time until reply
3. Research current devices and parts to get better idea of products
[Still need best parts]
Still need to contact the last 3 on Bimle's list and search the websites thoroughly
Hi, I am looking for microblowers or miniature air pumps for a smart necklace that emits a scent in a controlled fashion in response to certain criteria. In this order of importance, I am looking for pumps that are as small as possible, quiet, and have low power consumption. Generating high amount of pressure is not necessary. It would be nice if it could tolerate the passage of essential oil vapor through the pump, but it is not mandatory as I can use a separate valve instead. I don't have an exact specificatin for flow rate, but it needs to be enough to blow the scent from a wick on the necklace to the wearer's nose.
|  |  |  | Research current devices and what they use | [8 empty] | `
Countermeasures | Contacted Companies
| Company | Contact | Response |  | Note |  | Link
| Diaphragm Pumps ¦ KNF | contact 9-5 - left message | None yet
| Gas Pumps (schwarzer.com) |  |  |  | pumps are too big
| CurieJet | Contacted | Contacted
| Takasago | Contacted | email response
| Lee | Contacted | call/email response |  | need to respond with fan/pump flowrate and hole size |  | https://mail.google.com/mail/u/0/#inbox/FMfcgzGxRxDZPRFztpSmjqpnztwrMtDv
| Murata | Contacted | None yet
| Pelonis | Contacted | None yet
| Implementation Plan | [5 empty] | Order of Execution
| Activity |  |  |  | Who? |  | Item |  | Due To |  | Status
| Research current devices | [5 empty] | Detemine initial pump/fan
| Contact engineering salespeople - pumps, battery, valves | [5 empty] | Determine power draw of components
| ask about power consumption, design choices, technical requirements, etc. with PCB designer | [5 empty] | Contact PCB designer to determine power draw of PCB. Talk about initial testing with nano
| Produce horizontally directed tubular structures with a flat side to lay on, and a curve that follows the jaw line (curve concave). Make both ends of the necklace attach to the necklace so that it is less likely to flop around and hit you in the face. Round ones can work, but the pendant should still be in the middle with two opposite attachment points for the necklace. | [5 empty] | Determine battery
Order parts
Tests parts with nano
Results | Result Summary (Including benefits obtained) | [5 empty] | Follow-up Actions
[7 empty] | What? |  |  | Who? | When? | Status

## A3 Problem Solving - Advanced
| Reference #: |  | Process owner: |  | Leader/facilitator: |  | Note taker: |  | Revision #: |  | Date:
Problem Definition | [5 empty] | A3 | Problem Solving
| Title | [5 empty] | Scope (Location, area, line, department, boundaries, etc.)
| Process Name |  |  | Process Map Exist? |  |  | Start Date |  |  | Estimated Completion Date
| Problem Description (Initial condition) | [5 empty] | Problem Category
[9 empty] | Quality |  | Waste and efficiency
[9 empty] | Cost |  | Health and safety
[9 empty] | Delivery |  | Customer satisfaction
[9 empty] | Moral |  | Other
| Goal (Target condition) | [5 empty] | Expected Benefits (Hard savings and soft savings)
Key Metrics (Include baseline and improvement goals)
| Additional documents can be attached to this form including before photos, drawings and a more detailed cost benefit analysis. | [9 empty] | Attachments?
Cause Analysis | Cause and Effect (Brainstorming - Prioritize the causes) | [5 empty] | 5 Whys (Brainstorming - Ask, why did this occur?)
Why 1
Why 2
Why 3
[6 empty] | [ ] | Why 4
Why 5
Cause Analysis Summary (Prioritize in order of importance - % Contribution)
Will addressing this cause(s) solve the problem permanently?
| Additional documents can be attached to this form including a more in-depth root cause analysis and the prioritization method used. | [9 empty] | Attachments?
Countermeasures |  |  |  | Proceed with solving the problem? |  |  | List of Countermeasures and Quick Wins (Brainstorming - Relate to the root causes)
| Decision and Agreements (Explain the reasoning behind the decision) | [5 empty] | Priority |  | Ease | Cost | Impact | Score
Solution Description
Team Members
| Name |  |  | Role |  |  | Name |  |  | Role
Implementation Plan (Implement countermeasures)
| Activity |  |  |  | Who? |  | Start Date |  | Due To |  | Status
| Additional documents can be attached to this form including a more detailed implementation plan. | [9 empty] | Attachments?
Results |  | Improvement implemented? |  |  | Results verified? |  | Key Metrics
|  | Target achieved? |  |  | Can the solution be deployed? |  | Metric |  | Baseline | Goal | Current | Variance %
Result Summary (Including benefits obtained)
| Verification Comments (Assess countermeasures) | [5 empty] | Follow-up Actions (sustaining actions to be taken - actions for establishing controls)
[7 empty] | What? |  |  | Who? | When? | Status
Controls Required (SOP, training, audits, SPC charts, visual controls, mistake proofing, PM, etc.)
| Additional documents can be attached to this form including the after photos | [9 empty] | Attachments?
| Signatures: | Leader: |  |  | Analyst: |  |  | Process Owner: |  |  | Champion:
Continuous Improvement Toolkit . www.citoolkit.com
Guide:
The A3 Template provides a simple and consistent approach to problem solving throughout the organization using the logical thinking process.
It is an effective way in bringing together many of the tools used in problem solving and process improvement.
It is composed of a sequence of sections:
1 - Establish the business context and describe the current and the target conditions.
2- Establish causality.
3- Identify and develop countermeasures.
4- Verify results and create a follow-up process.